## Sheet1
Phase/Activity | Description | Estimated Hours | BABOK Knowledge Area
Planning and stakeholder analysis | Planning BA tasks, identifying stakeholders, defining deliverables | 6 | Business Analysis Planning and Monitoring
Data gathering and communication with stakeholder | Communicating with the accountant, gathering business context | 10 | Elicitation and Collaboration
Requirement tracking and traceability | Tracing, maintaining, and validating data/report requirements | 6 | Requirements Life Cycle Management
Problem and opportunity analysis | Understanding business needs and current state analysis | 6 | Strategy Analysis
Building dashboards and report design | Data cleaning, SQL queries, Power BI visuals, KPIs, layout design | 14 | Requirements Analysis and Design Definition
Validating and evaluating Power BI solution | Validating dashboard insights, getting feedback, refinements | 8 | Solution Evaluation